## ACS Build
Title | Status | Category | Type | Description | Assigned To | Assignee Type | Location | Location Details | Due Date | Start Date | Root Cause Category | Root Cause | Building Name | Information Category | From | To | Design Phase
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | HCC SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | HCC SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | EGR SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | EGR SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | GIS SUBSTATION - CCPP | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | CCPP SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | CCPP SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Switchgear Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Switchgear Room | [8 empty] | CCPP SUBSTATION - Module C | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | HCC SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | HCC SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | EGR SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | EGR SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | GIS SUBSTATION - CCPP | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | CCPP SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | CCPP SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | CCPP SUBSTATION - Module C | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | LCR 31 - HCC | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | LCR 32 - EGR | ARCH | ELE | BLD | For Concept
Battery Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of battery rack inside Battry Room | [8 empty] | LCR 30 - CCPP | ARCH | ELE | BLD | For Concept
UPS Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside UPS room | [8 empty] | LCR 31 - HCC | ARCH | ELE | BLD | For Concept
UPS Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside UPS room | [8 empty] | LCR 32 - EGR | ARCH | ELE | BLD | For Concept
UPS Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside UPS room | [8 empty] | LCR 30 - CCPP | ARCH | ELE | BLD | For Concept
Telecom Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel and equipment layout inside Telecom room | [8 empty] | LCR 31 - HCC | ARCH | ELE | BLD | For Concept
Telecom Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel and equipment layout inside Telecom room | [8 empty] | LCR 32 - EGR | ARCH | ELE | BLD | For Concept
Telecom Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel and equipment layout inside Telecom room | [8 empty] | LCR 30 - CCPP | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | HCC SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | HCC SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | EGR SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | EGR SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | GIS SUBSTATION - CCPP | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | CCPP SUBSTATION - Module A | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | CCPP SUBSTATION - Module B | ARCH | ELE | BLD | For Concept
Transformer Yard Layout - Equipment Size and Oil Volume | Draft | Information Control Sheet | Information Control Sheet | Size of Transformer and clearance with Firewall (for preparation of conceptual drawing). | [8 empty] | CCPP SUBSTATION - Module C | ARCH | ELE | BLD | For Concept
Control Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside Control room | [8 empty] | LCR 31 - HCC | ARCH | INST | BLD | For Concept
Control Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside Control room | [8 empty] | LCR 32 - EGR | ARCH | INST | BLD | For Concept
Control Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Panel layout inside Control room | [8 empty] | LCR 30 - CCPP | ARCH | INST | BLD | For Concept
Rack Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Rack room | [8 empty] | LCR 31 - HCC | ARCH | INST | BLD | For Concept
Rack Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Rack room | [8 empty] | LCR 32 - EGR | ARCH | INST | BLD | For Concept
Rack Room Layout - Equipment Size and Weight | Draft | Information Control Sheet | Information Control Sheet | Layout, size and weight of panels inside Rack room | [8 empty] | LCR 30 - CCPP | ARCH | INST | BLD | For Concept
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | HCC SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | HCC SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | EGR SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | EGR SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | GIS SUBSTATION - CCPP | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | CCPP SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | CCPP SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Switchgear Room - Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the floor inside Switchgear room | [8 empty] | CCPP SUBSTATION - Module C | ARCH | ELE | BLD | For Detail
Telecom Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the raised access floor inside Telecom room | [8 empty] | LCR 31 - HCC | ARCH | ELE | BLD | For Detail
Telecom Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the raised access floor inside Telecom room | [8 empty] | LCR 32 - EGR | ARCH | ELE | BLD | For Detail
Telecom Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Electrical cable entry on the raised access floor inside Telecom room | [8 empty] | LCR 30 - CCPP | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | HCC SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | HCC SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | EGR SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | EGR SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | GIS SUBSTATION - CCPP | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | CCPP SUBSTATION - Module A | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | CCPP SUBSTATION - Module B | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | CCPP SUBSTATION - Module C | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 31 - HCC | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 32 - EGR | ARCH | ELE | BLD | For Detail
Electrical/ Telecom Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Electrical cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 30 - CCPP | ARCH | ELE | BLD | For Detail
Control/ Rack Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Instrument cable entry on the raised access floor for Rack Room, Control Room | [8 empty] | LCR 31 - HCC | ARCH | INST | BLD | For Detail
Control/ Rack Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Instrument cable entry on the raised access floor for Rack Room, Control Room | [8 empty] | LCR 32 - EGR | ARCH | INST | BLD | For Detail
Control/ Rack Room - Raised Access Floor Opening | Draft | Information Control Sheet | Information Control Sheet | Instrument cable entry on the raised access floor for Rack Room, Control Room | [8 empty] | LCR 30 - CCPP | ARCH | INST | BLD | For Detail
Instrument Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Instrument cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 31 - HCC | ARCH | INST | BLD | For Detail
Instrument Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Instrument cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 32 - EGR | ARCH | INST | BLD | For Detail
Instrument Cable Tray Route - Internal Wall | Draft | Information Control Sheet | Information Control Sheet | Instrument cable conduit/ tray layout incl. penetration of internal wall | [8 empty] | LCR 30 - CCPP | ARCH | INST | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | HCC SUBSTATION - Module A | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | HCC SUBSTATION - Module B | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | EGR SUBSTATION - Module A | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | EGR SUBSTATION - Module B | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | GIS SUBSTATION - CCPP | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | CCPP SUBSTATION - Module A | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | CCPP SUBSTATION - Module B | STR Foundation | ELE | BLD | For Detail
Transformer Yard - Anchor, Rail, Bus duct support foundation etc. | Draft | Information Control Sheet | Information Control Sheet | Anchor (Rail), Weight and Bus Duct Foundation etc. | [8 empty] | CCPP SUBSTATION - Module C | STR Foundation | ELE | BLD | For Detail
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | HCC SUBSTATION - Module A | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | HCC SUBSTATION - Module B | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | EGR SUBSTATION - Module A | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | EGR SUBSTATION - Module B | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | GIS SUBSTATION - CCPP | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | CCPP SUBSTATION - Module A | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | CCPP SUBSTATION - Module B | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | CCPP SUBSTATION - Module C | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | LCR 31 - HCC | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | LCR 32 - EGR | STR Super structure | HSE | BLD | For Concept
Blast Resistant requirement (BLD Name, Side On Pressure (psi), Response Range, Door performance req) | Draft | Information Control Sheet | Information Control Sheet | Need to align with HSE about contents of Blast Resistant Analysis report (Duration/ Over Pressure/ Response Range) | [8 empty] | LCR 30 - CCPP | STR Super structure | HSE | BLD | For Concept
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | HCC SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | HCC SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | EGR SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | EGR SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | GIS SUBSTATION - CCPP | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | CCPP SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | CCPP SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | CCPP SUBSTATION - Module C | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | LCR 31 - HCC | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | LCR 32 - EGR | STR Super structure | ELE | BLD | For Detail
Electrical Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Mainly for Bus Duct route *In case of raised floor type, cable bedding level is recommended to be aligned at the same time for construction. | [8 empty] | LCR 30 - CCPP | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | HCC SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | HCC SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | EGR SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | EGR SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | GIS SUBSTATION - CCPP | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | CCPP SUBSTATION - Module A | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | CCPP SUBSTATION - Module B | STR Super structure | ELE | BLD | For Detail
Electrical/ Telecom Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of electrical panel supports inside Rack room | [8 empty] | CCPP SUBSTATION - Module C | STR Super structure | ELE | BLD | For Detail
Instrument Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Layout of MCT, embedded plate for Cable trays etc. | [8 empty] | LCR 31 - HCC | STR Super structure | INST | BLD | For Detail
Instrument Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Layout of MCT, embedded plate for Cable trays etc. | [8 empty] | LCR 32 - EGR | STR Super structure | INST | BLD | For Detail
Instrument Cable Route - External Wall | Draft | Information Control Sheet | Information Control Sheet | Layout of MCT, embedded plate for Cable trays etc. | [8 empty] | LCR 30 - CCPP | STR Super structure | INST | BLD | For Detail
Instrument Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of instrument panel supports inside Rack room | [8 empty] | LCR 31 - HCC | STR Super structure | INST | BLD | For Detail
Instrument Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of instrument panel supports inside Rack room | [8 empty] | LCR 32 - EGR | STR Super structure | INST | BLD | For Detail
Instrument Equipment Support | Draft | Information Control Sheet | Information Control Sheet | Layout, size and details of instrument panel supports inside Rack room | [8 empty] | LCR 30 - CCPP | STR Super structure | INST | BLD | For Detail
Battery - Number of Cells and Charging Current | Draft | Information Control Sheet | Information Control Sheet | Battery characteristic for ventilation | [8 empty] | LCR 31 - HCC | HVAC | ELE | BLD | For Detail
Battery - Number of Cells and Charging Current | Draft | Information Control Sheet | Information Control Sheet | Battery characteristic for ventilation | [8 empty] | LCR 32 - EGR | HVAC | ELE | BLD | For Detail
Battery - Number of Cells and Charging Current | Draft | Information Control Sheet | Information Control Sheet | Battery characteristic for ventilation | [8 empty] | LCR 30 - CCPP | HVAC | ELE | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | HCC SUBSTATION - Module A | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | HCC SUBSTATION - Module B | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | EGR SUBSTATION - Module A | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | EGR SUBSTATION - Module B | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | GIS SUBSTATION - CCPP | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | CCPP SUBSTATION - Module A | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | CCPP SUBSTATION - Module B | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | CCPP SUBSTATION - Module C | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | LCR 31 - HCC | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | LCR 32 - EGR | HVAC | ELE/ INST/ LABO | BLD | For Detail
Heat Dissipation - Electrical/ Instrument/ Labo Equipment | Draft | Information Control Sheet | Information Control Sheet | Heat generation of each equipment | [8 empty] | LCR 30 - CCPP | HVAC | ELE/ INST/ LABO | BLD | For Detail
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | HCC SUBSTATION - Module A | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | HCC SUBSTATION - Module B | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | EGR SUBSTATION - Module A | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | EGR SUBSTATION - Module B | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | GIS SUBSTATION - CCPP | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | CCPP SUBSTATION - Module A | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | CCPP SUBSTATION - Module B | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | CCPP SUBSTATION - Module C | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | LCR 31 - HCC | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | LCR 32 - EGR | PLUM | BLD | PEN/ FIRE | For Concept
Building Utility Demand | Draft | Information Control Sheet | Information Control Sheet | Required utilities (to PEN) and fire water (to FIRE) | [8 empty] | LCR 30 - CCPP | PLUM | BLD | PEN/ FIRE | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | HCC SUBSTATION - Module A | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | HCC SUBSTATION - Module B | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | EGR SUBSTATION - Module A | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | EGR SUBSTATION - Module B | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | GIS SUBSTATION - CCPP | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | CCPP SUBSTATION - Module A | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | CCPP SUBSTATION - Module B | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | CCPP SUBSTATION - Module C | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | LCR 31 - HCC | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | LCR 32 - EGR | PLUM | BLD | PEN/ CVL | For Concept
Flow Rate of Building Drainage | Draft | Information Control Sheet | Information Control Sheet | Estimated Flow Rate and Drainage volume | [8 empty] | LCR 30 - CCPP | PLUM | BLD | PEN/ CVL | For Concept
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | HCC SUBSTATION - Module A | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | HCC SUBSTATION - Module B | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | EGR SUBSTATION - Module A | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | EGR SUBSTATION - Module B | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | GIS SUBSTATION - CCPP | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | CCPP SUBSTATION - Module A | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | CCPP SUBSTATION - Module B | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | CCPP SUBSTATION - Module C | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | LCR 31 - HCC | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | LCR 32 - EGR | PLUM | BLD | PIP/ CVL | For Detail
Utility and Sewer Tie-in Location | Draft | Information Control Sheet | Information Control Sheet | Coordinates and elevation of tie-in point, piping diameter and material | [8 empty] | LCR 30 - CCPP | PLUM | BLD | PIP/ CVL | For Detail
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | HCC SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | HCC SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | EGR SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | EGR SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | GIS SUBSTATION - CCPP | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | CCPP SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | CCPP SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | CCPP SUBSTATION - Module C | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | LCR 31 - HCC | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | LCR 32 - EGR | ELEC/ TELE | BLD | ELEC | For Concept
Power Supply Scheme | Draft | Information Control Sheet | Information Control Sheet | Type of Cable, Voltage, Power Source etc. | [8 empty] | LCR 30 - CCPP | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | HCC SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | HCC SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | EGR SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | EGR SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | GIS SUBSTATION - CCPP | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | CCPP SUBSTATION - Module A | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | CCPP SUBSTATION - Module B | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | CCPP SUBSTATION - Module C | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | LCR 31 - HCC | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | LCR 32 - EGR | ELEC/ TELE | BLD | ELEC | For Concept
Electrical Load for Building Services | Draft | Information Control Sheet | Information Control Sheet | Normally to fill out and inform as per format by ELEC | [8 empty] | LCR 30 - CCPP | ELEC/ TELE | BLD | ELEC | For Concept
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | HCC SUBSTATION - Module A | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | HCC SUBSTATION - Module B | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | EGR SUBSTATION - Module A | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | EGR SUBSTATION - Module B | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | GIS SUBSTATION - CCPP | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | CCPP SUBSTATION - Module A | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | CCPP SUBSTATION - Module B | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | CCPP SUBSTATION - Module C | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | LCR 31 - HCC | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | LCR 32 - EGR | Fire Protection | BLD | FIRE/ INST | For Detail
Interface Signal for Building Fire & Gas and HVAC | Draft | Information Control Sheet | Information Control Sheet | Terminal Block Number for Junction Box (cannot inform at the first issue as normally is determined by subcontractor) | [8 empty] | LCR 30 - CCPP | Fire Protection | BLD | FIRE/ INST | For Detail
Junction Box for Building Signal (Location) | Draft | Information Control Sheet | Information Control Sheet | Interface Junction Box information for Instrument. To request INST to incorporate into panel layout, if possible. | [8 empty] | LCR 31 - HCC | Fire Protection | INST | BLD | For Detail
Junction Box for Building Signal (Location) | Draft | Information Control Sheet | Information Control Sheet | Interface Junction Box information for Instrument. To request INST to incorporate into panel layout, if possible. | [8 empty] | LCR 32 - EGR | Fire Protection | INST | BLD | For Detail
Junction Box for Building Signal (Location) | Draft | Information Control Sheet | Information Control Sheet | Interface Junction Box information for Instrument. To request INST to incorporate into panel layout, if possible. | [8 empty] | LCR 30 - CCPP | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | HCC SUBSTATION - Module A | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | HCC SUBSTATION - Module B | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | EGR SUBSTATION - Module A | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | EGR SUBSTATION - Module B | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | GIS SUBSTATION - CCPP | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | CCPP SUBSTATION - Module A | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | CCPP SUBSTATION - Module B | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | CCPP SUBSTATION - Module C | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | LCR 31 - HCC | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | LCR 32 - EGR | Fire Protection | INST | BLD | For Detail
Gas Detector/ Horn Location | Draft | Information Control Sheet | Information Control Sheet | If applicable, installation detail to be incorporated | [8 empty] | LCR 30 - CCPP | Fire Protection | INST | BLD | For Detail